## TIMELINE_ROYAL_SHOPIFY_JDA_INTE
ROYAL STORE SHOPIFY x JDA INTEGRATION
Implementation Timeline
Start Date: | January 10, 2026
Target Completion: | May 9, 2026
Duration: | 18 weeks
PHASE TIMELINE
Phase | Description | Duration | Start Date | End Date | Week Range | Status
1 | Foundation & Setup | 2 weeks | Jan 2, 2026 | Jan 17, 2026 | Week 1-2 | In Progress (Partial)
2 | JDA Database Connection | 2 weeks | Jan 20, 2026 | Jan 31, 2026 | Weeks 3-4 | Pending
3 | Store Locations Module | 2 weeks | Feb 3, 2026 | Feb 14, 2026 | Weeks 5-6 | Pending
4 | Products Module | 3 weeks | Feb 17, 2026 | Mar 7, 2026 | Weeks 7-9 | Pending
5 | Inventory Module | 3 weeks | Mar 10, 2026 | Mar 28, 2026 | Weeks 10-12 | Pending
6 | User Registration Module | 2 weeks | Mar 31, 2026 | Apr 11, 2026 | Weeks 13-14 | Pending
7 | Shopify Theme Updates | 1 week | Apr 14, 2026 | Apr 18, 2026 | Week 15 | Pending
8 | Sync Management & Dashboard | 1 week | Apr 21, 2026 | Apr 25, 2026 | Week 16 | Pending
9 | Testing & Go-Live | 2 weeks | Apr 28, 2026 | May 9, 2026 | Weeks 17-18 | Pending
GANTT VIEW
Phase | Description | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
1 | Foundation & Setup | bar: W1 to W2
2 | JDA Database Connection | bar: W3 to W4
3 | Store Locations Module | bar: W5 to W6
4 | Products Module | bar: W7 to W9
5 | Inventory Module | bar: W10 to W12
6 | User Registration Module | bar: W13 to W14
7 | Shopify Theme Updates | bar: W15
8 | Sync Management & Dashboard | bar: W16
9 | Testing & Go-Live | bar: W17 to W18
Timeline subject to adjustment based on access to JDA systems and dependencies.
Timeline already considers other concurrent tasks including Shopify theme feature requests and maintenance for joelsplace.com
Weekly progress may vary based on support requests and urgent fixes for both stores.
This timeline is dedicated specifically to the JDA integration project deliverables.